## Sheet1
Sprint ceremonies | Day of the week | Time | Purpose
Daily Scrum | MTWRF (Daily) | 9:45am EST (15min) | Daily Communications: Done, Planned, Blockers
Sprint Planning | W (Every 2 week) | 9:30am EST (4hrs) | Team creates, plans, estimates and assigns tasks for each Current Sprint User stories
Sprint Demo | T ( Every 2 weeks) | 10:00am EST ( 2hrs) | All the teams have 10min to Demo work done
Sprint Retrospective | W (Every 2 week) | Afternoon 1hr | Team Retro on how sprint went
Sprint Priority | T ( Every 2 weeks) | Afternoon 1hr | Team and PO confirms the User Story Priority for the next Sprint
Grooming Session | W (Every week) / R(Every Week) | 4pm EST (1hr) / 9am EST (1hr) | Groom user stories for next Sprint. Note: No Groom on Sprint Planning Day
Scrum of Scrums (SOS) | T ( Every 2 week) | 10:30am (1hr) | Scrum Masters / ? Report to project the status of the Team
PO Meeting | MTWRF (Daily) | 12:30pm (1hr) | Product Owner (PO) Meeting